## Description
JSON tools
Application for programmers who need to reformat or filter data structures saved in JSON format and to compare the structures with each other. JSON tools application allows you to both minify the unminified JSON representation, as well as the reverse operation (with any blanks and new lines added). The application will be available via GUI, as well as as a remote API, so it can be integrated with existing tools.
Note: we do not require creating your own parser for JSON representation, you can successfully use libraries - e.g. Jakson library (mapping objects to JsonNode type).

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As an external software developer, I can use the available functions remotely via REST to be able to integrate the tool with other applications. | 20 | 10 | 1 | o Input in JSON format containing the structure to be transformed o Input transformed to an object model o Output in JSON format o REST API allows you to run any currently implemented function.
As a developer, I can get a minified JSON structure from JSON full format to reduce data size. | 12 | 6 | 1 | o The shape of the data does not change o The result does not contain unnecessary spaces o The result fits to one line o Error reported for incorrect JSON
As a developer, I can get the full structure in JSON format from minified JSON format to improve the readability of the data. | 12 | 6 | 1 | o The shape of the data does not change o The result is properly indented o Error reported for incorrect JSON
As a developer, I can get a JSON-formatted structure with only certain keys to simplify the structure. | 10 | 4 | 1 | o The shape of the data does not change o All keys are removed from JSON objects except those passed on input o Error reported for incorrect JSON
As a developer, I can get a JSON structure without specific keys to simplify the structure. | 10 | 4 | 1 | o The shape of the data does not change o JSON objects have only selected keys (all others are removed) o Error reported for incorrect JSON
As a developer, I can compare two texts (e.g. representing the data structure in JSON formats) expecting the application to show lines where there is a difference. | 9 | 5 | 1 | o Correctly reported lines with differences o No differences are found if both texts are blank o If one text is blank, the whole other is marked as difference
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later
New Product Backlog items
As a developer, I can validate a JSON structure against a predefined schema to ensure data integrity before processing. | 15 | 2 | 1 | - Input accepts JSON data and JSON schema - Validation returns true/false result - Detailed error messages provided for validation failures - REST API endpoint available for remote validation - Error reported for malformed JSON or schema
As a data analyst, I can convert JSON data to CSV format to use the data in spreadsheet applications and reporting tools. | 8 | 1 | 1 | - Input accepts JSON array of objects - Output generates properly formatted CSV - Column headers derived from JSON object keys - Handles nested objects by flattening structure - Handles missing fields with empty values - Error reported for incompatible JSON structures
As a developer, I can perform operations on JSON arrays (filter, sort, map) to manipulate collections of data efficiently | 11 | 2 | 1 | - Input accepts JSON array and operation type (filter/sort/map) - Filter operation accepts criteria for element selection - Sort operation accepts field name and direction (asc/desc) - Map operation accepts transformation rules - Output maintains JSON format - Error reported for non-array input when array is expected
As a developer, I can process multiple JSON files simultaneously to improve efficiency when handling large datasets. | 10 | 2 | 1 | - Input accepts multiple JSON files or file patterns - Same operation applied to all files - Results returned as array of processed outputs - Processing continues even if individual files fail - Summary report shows success/failure count - Error details provided for failed files
As a user, I can view the history of JSON transformations and undo previous operations to recover from mistakes. | 7 | 1 | 1 | - System maintains history of last 10 operations - User can view list of previous transformations - Undo function restores previous JSON state - Redo function available after undo - History cleared when new JSON input provided - Visual indicator shows current position in history

## Sprint #1 Backlog
Sprint Goal: Do everything from DoD
Product Backlog Item | Tasks | Labour intensity
As an external software developer, I can use the available functions remotely via REST to be able to integrate the tool with other applications. |  | 10
| Design REST API endpoints | 2
| Implement REST controller logic | 2
| Transform input to object model | 2
| Output response in JSON | 2
| Write API test | 2
As a developer, I can get a minified JSON structure from JSON full format to reduce data size. |  | 6
| Implement minification logic | 2
| Ensure shape of data remains unchanged | 1
| Remove unnecessary spaces | 1
| Write error handling for incorrect JSON | 2
As a developer, I can get the full structure in JSON format from minified JSON format to improve the readability of the data. |  | 6
| Implement unminification logic | 2
| Ensure shape of data remains unchanged | 1
| Implement pretty-print logic | 2
| Write error handling | 1
As a developer, I can get a JSON-formatted structure with only certain keys to simplify the structure. |  | 4
| Implement key filtering logic | 1
| Ensure shape of data remains unchanged | 1
| Remove all keys except those passed in input | 1
| Error handling | 1
As a developer, I can get a JSON structure without specific keys to simplify the structure. |  | 4
| Implement key exclusion logic | 1
| Ensure shape of data remains unchanged | 1
| Remove specified keys | 1
| Error handling | 1
As a developer, I can compare two texts (e.g. representing the data structure in JSON formats) expecting the application to show lines where there is a difference. |  | 5
| Implement text comparison logic | 2
| Report lines with differences | 1
| Handle blank text cases | 1
| If one text is blank, the whole other is marked as difference | 1
Setting up Github repository |  | 0.013889
| Create repository | 0.0034722
| Create TODO list with GitHub Projects | 0.0069444
| Add everyone as collaborators | 0.0034722
Creating UML |  | 0.23611
| Think about project structure | 0.125
| Draw UML diagrams | 0.11111